## Sheet1
| TASK 1 |  |  | TASK 2
| CREATING WEB APP |  |  | STORE DATA
REGISTER AND LOGIN | DESIGN | DEVELOPMENT | TESTING | EMPLOYEE TABLE | Nov 2 2019 - Dec 6 2019
| DESIGN OF REGISTER FORM Oct 14 2019- oct 28 2019 | Oct 29 2019- Nov 29 2019 | Nov 30 2019- Dec 06 2019
| LOGIN FORM Oct 14 2019- oct 28 2019 | Oct 29 2019- Nov 29 2019 | Nov 30 2019- Dec 06 2019
HOME SCREEN OR SEARCH SCREEN | DESIGN | DEVELOPMENT | TESTING | SYSTEM TABLE | Dec 9 2019 - Dec 31 2019
| NAVIGATION Dec 9 2019 - Dec 20 2019 | Dec 23 2019 - Jan 17 2020 | Jan 20 2020 - Jan 28 2020
| SEARCH SCREEN Dec 9 2019 - Dec 20 2019 | Dec 23 2019 - Jan 17 2020 | Jan 20 2020 - Jan 28 2020
HELP SCREEN | DESIGN | DEVELOPMENT | TESTING
| CONTENTS Feb 3 2020 - Feb 17 2020 | Feb 18 2020 - Mar 9 2020 | Mar 10 2020 - Mar 19 2020 | STATUS TABLE | Jan 1 2020 - Feb 14 2020
LOGOUT SCREEN | DESIGN | DEVELOPMENT | TESTING
| LOGOUT FORM Mar 23 2020 - Apr 9 2020 | Apr 10 2020 - May 10 2020 | May 11 2020 - May 19 2020